## Project schedule
| CIVE 202 Project #2 | [5 empty] | Project start: | [7 empty] | 2026-02-06 | [19 empty] | DEPENDENCIES
| Jacob Oetken, Abbas Bashir, Anicet Atikpohou, Michael Albracht | [5 empty] | Display week: | [7 empty] | 1 | [20 empty] | Right Symbol is Dependent Upon Left Symbol
[7 empty] | 2026-02-02 | [6 empty] | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23
| TASK | ASSIGNED TO | PROGRESS | START | END |  | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01
[7 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
| Github Repository | [33 empty] | FINAL REPORT | GITHUB REPO | CODE DOCUMENT | ANNOTATED CD
| Create Github | Jacob | 100% | 2026-02-13 | 2026-02-16 | 4
| Create README Document | Abbas | 100% | 2026-02-16 | 2026-02-24 | 9
| Combine information/Files | ALL | 100% | 2026-02-20 | 2026-02-24 | 5
| Upload All Files to Github | Jacob | 100% | 2026-02-24 | 2026-02-24 | 1
| Submit | Jacob | 100% | 2026-02-24 | 2026-02-24 | 1
Scope of Work
| Identify Tasks | ALL | 100% | 2026-02-06 | 2026-02-06 | 1
| Create SOW | Jacob | 100% | 2026-02-13 | 2026-02-18 | 6
| Task 1-2 | Abbas/Jacob | 100% | 2026-02-13 | 2026-02-20
| Task 2-4 | Anicet/Michael | 100% | 2026-02-16 | 2026-02-20 | 5
| Review | ALL | 100% | 2026-02-16 | 2026-02-20 | 5
| Submit SOW | Jacob | 100% | 2026-02-20 | 2026-02-20 | 1
Gantt Chart
| Identify Tasks | ALL | 100% | 2026-02-06 | 2026-02-09 | 4
| Create Gantt Chart | Jacob | 100% | 2026-02-10 | 2026-02-11 | 2
| Review | ALL | 100% | 2026-02-12 | 2026-02-13 | 2
| Turn in Gantt Chart | Jacob | 100% | 2026-02-12 | 2026-02-13 | 2
Mix Scenarios Research
| Research Mix 1 | Jacob | 100% | 2026-02-10 | 2026-02-13 | 4
| Research Mix 2 | Abbas | 100% | 2026-02-13 | 2026-02-16 | 4
| Research Mix 3 | Anicet | 100% | 2026-02-16 | 2026-02-19 | 4
| Research Mix 4 | Michael | 100% | 2026-02-19 | 2026-02-22 | 4
| Discuss/Apply To Report | ALL | 100% | 2026-02-22 | 2026-02-24 | 3
Python Code
| LAB 1 Material | Michael | 100% | 2026-02-06 | 2026-02-13 | 8
| LAB 2 Material | Abbas | 100% | 2026-02-13 | 2026-02-20
| LAB 3 Material | Anicet | 100% | 2026-02-20 | 2026-02-24
| Combine/Polish | Jacob | 100% | 2026-02-20 | 2026-02-24
| Review and Submit | ALL | 100% | 2026-02-21 | 2026-02-24
Annotated Code Document
| LAB 1 Material | Michael | 100% | 2026-02-09 | 2026-02-13 | 5
| LAB 2 Material | Abbas | 100% | 2026-02-13 | 2026-02-20
| LAB 3 Material | Anicet | 100% | 2026-02-20 | 2026-02-24
| Combine/Polish | Jacob | 100% | 2026-02-20 | 2026-02-24
| Review and Submit | ALL | 100% | 2026-02-21 | 2026-02-24
Written Report
| Analyze Outputs | Jacob | 100% | 2026-02-08 | 2026-02-11 | 4
| Create Document to Standards | Abbas | 100% | 2026-02-11 | 2026-02-19
| Review | ALL | 100% | 2026-02-19 | 2026-02-24
| Submit | Jacob | 100% | 2026-02-20 | 2026-02-24
Formulas:
Project start: = [Project start:, row below]
R
R
R
_
_
R
R
R
G
G
G
G
C
C
A
C
A